## Project Gantt
Abhijatri:Execution Gantt Chart
CSE 3102 • ChoturMatra • M1: 2 Nov • 50–60%: 7 Dec • Testing: 4–11 Jan • Final: 17/18 Jan
Fixed milestone dates; early completion is allowed. Work is balanced by role. | [13 empty] | ■ Scheduled task ◆ Gate / milestone Update Status as work progresses.
ID | Phase | Type | Workstream | Task / Deliverable | Primary Owner | Support | Effort | Start | End | Depends On | Status | Acceptance / Evidence | Risk / Notes | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18
F01 | Foundation | Task | Scope | Freeze first-release scope and acceptance gates | Shahriar Islam | All | 4 | 2026-10-12 | 2026-10-13 |  | Not started | Approved scope and definition of done | Do not add cost estimator before M1 | bar: 2026-10-12
F02 | Foundation | Task | Architecture | Define architecture, database schema and API contract | Syed Muhtasim Alam | Abdullah, Shahriar | 6 | 2026-10-12 | 2026-10-14 | F01 | Not started | Versioned API contract and ERD reviewed | Resolve auth/offline boundaries early | bar: 2026-10-12
F03 | Foundation | Task | UX and i18n | Create bilingual information architecture and UI component plan | Abdullah Bin Sorwar Choudhury | Shahriar | 4 | 2026-10-12 | 2026-10-14 | F01 | Not started | Bangla-default flows and component map approved | Use system font fallback | bar: 2026-10-12
F04 | Foundation | Task | Quality | Create master test plan and requirement traceability matrix | Md. Irfan Iqbal | All | 4 | 2026-10-12 | 2026-10-15 | F01 | Not started | Every M1 requirement mapped to test IDs | Include offline and role tests | bar: 2026-10-12
F05 | Foundation | Task | Content | Define source/date/licence template for destinations | Shahriar Islam | Irfan | 3 | 2026-10-12 | 2026-10-14 | F01 | Not started | Template captures source, date, language and licence | No scraped images | bar: 2026-10-12
F06 | Foundation | Task | Engineering | Set up repositories, CI checks and shared environments | Syed Muhtasim Alam | Abdullah | 5 | 2026-10-12 | 2026-10-15 | F02 | Not started | Frontend/backend build and test in CI | Document environment variables | bar: 2026-10-12
F07 | Foundation | Task | Security | Create privacy, access-control and cache-safety checklist | Md. Irfan Iqbal | Muhtasim | 3 | 2026-10-13 | 2026-10-16 | F02 | Not started | Checklist covers private data and public caches | No raw NID in M1 | bar: 2026-10-12
R01 | M1: Destination + Reviews | Task | Content | Prepare one complete bilingual seeded destination | Shahriar Islam | Irfan | 5 | 2026-10-15 | 2026-10-22 | F05 | Not started | Source-dated Bangla/English content and contacts pass review | One complete destination before adding more | bar: 2026-10-12 to 2026-10-19
R02 | M1: Destination + Reviews | Task | Destination API | Build destination, advisory and contact data services | Syed Muhtasim Alam | Shahriar | 5 | 2026-10-15 | 2026-10-21 | F02,R01 | Not started | Validated list/detail endpoints with tests | Expired advisories not shown as current | bar: 2026-10-12 to 2026-10-19
R03 | M1: Destination + Reviews | Task | Destination UI | Build bilingual destination list and detail screens | Abdullah Bin Sorwar Choudhury | Shahriar | 5 | 2026-10-15 | 2026-10-22 | F03,R02 | Not started | Bangla-default pages with loading/error/empty states | English switch preserves context | bar: 2026-10-12 to 2026-10-19
R04 | M1: Destination + Reviews | Task | Authentication API | Implement registration, email verification, sign-in/out and reset | Syed Muhtasim Alam | Irfan | 5 | 2026-10-15 | 2026-10-22 | F02,F07 | Not started | Verified users can review; role checks tested | Use sandbox email if needed | bar: 2026-10-12 to 2026-10-19
R05 | M1: Destination + Reviews | Task | Authentication UI | Build account, verification and session screens | Abdullah Bin Sorwar Choudhury | Muhtasim | 4 | 2026-10-18 | 2026-10-23 | R04 | Not started | Accessible success/error/expired-token flows | Private responses never enter public cache | bar: 2026-10-12 to 2026-10-19
R06 | M1: Destination + Reviews | Task | Review rules | Finalize review fields, lifecycle and moderation policy | Shahriar Islam | Irfan, Muhtasim | 4 | 2026-10-15 | 2026-10-19 | F01,F04 | Not started | Pending/published/hidden/rejected/deleted rules documented | Rating uses published overall ratings only | bar: 2026-10-12 to 2026-10-19
R07 | M1: Destination + Reviews | Task | Review API | Implement structured review CRUD, ownership and pagination | Syed Muhtasim Alam | Irfan | 6 | 2026-10-18 | 2026-10-26 | R04,R06 | Not started | Create/read/edit/delete paths pass permission tests | Safe text rendering and validation | bar: 2026-10-12 to 2026-10-26
R08 | M1: Destination + Reviews | Task | Rating service | Implement Bayesian score and rating exclusion logic | Syed Muhtasim Alam | Irfan | 4 | 2026-10-22 | 2026-10-27 | R07 | Not started | Fixed prior documented; hidden/rejected excluded | Display review count with score | bar: 2026-10-19 to 2026-10-26
R09 | M1: Destination + Reviews | Task | Review UI | Build review form, list, filters and author controls | Abdullah Bin Sorwar Choudhury | Muhtasim | 6 | 2026-10-20 | 2026-10-27 | R05,R07 | Not started | Verified user completes review lifecycle | Reviews remain in submitted language | bar: 2026-10-19 to 2026-10-26
R10 | M1: Destination + Reviews | Task | Moderation UI | Build moderation queue, reason capture and audit view | Shahriar Islam | Abdullah, Muhtasim | 5 | 2026-10-20 | 2026-10-27 | R06,R07 | Not started | Moderator can approve/hide/reject with reason | Admin decisions are traceable | bar: 2026-10-19 to 2026-10-26
R11 | M1: Destination + Reviews | Task | Reporting API | Implement review reporting, moderation actions and audit log | Syed Muhtasim Alam | Shahriar, Irfan | 5 | 2026-10-22 | 2026-10-28 | R07,R10 | Not started | Report-to-decision flow and audit tests pass | Duplicate reports handled | bar: 2026-10-19 to 2026-10-26
R12 | M1: Destination + Reviews | Task | Offline foundation | Create installable PWA shell and cache public destination views | Abdullah Bin Sorwar Choudhury | Irfan | 5 | 2026-10-19 | 2026-10-25 | R03 | Not started | Selected page reopens on real phone in airplane mode | No private API caching | bar: 2026-10-19
R13 | M1: Destination + Reviews | Task | Offline pack | Store versioned destination pack and published-review snapshot in IndexedDB | Abdullah Bin Sorwar Choudhury | Muhtasim | 6 | 2026-10-23 | 2026-10-30 | R12,R14 | Not started | Download/open/delete/freshness states work offline | Request persistent storage; handle refusal | bar: 2026-10-19 to 2026-10-26
R14 | M1: Destination + Reviews | Task | Offline API | Implement pack manifest, version and freshness endpoints | Syed Muhtasim Alam | Abdullah | 4 | 2026-10-22 | 2026-10-27 | R02 | Not started | Pack exposes version, generated date and public content | Cache invalidation documented | bar: 2026-10-19 to 2026-10-26
R15 | M1: Destination + Reviews | Task | Offline drafts | Implement offline review drafts and idempotent reconnect submission | Abdullah Bin Sorwar Choudhury | Muhtasim, Irfan | 5 | 2026-10-25 | 2026-10-31 | R09,R13,R16 | Not started | Retry never creates duplicate review | Published-review edits remain online-only | bar: 2026-10-19 to 2026-10-26
R16 | M1: Destination + Reviews | Task | Idempotency API | Implement server-side idempotency-key storage and expiry | Syed Muhtasim Alam | Irfan | 3 | 2026-10-24 | 2026-10-28 | R07 | Not started | Unique constraint and retry tests pass | Document expiry policy | bar: 2026-10-19 to 2026-10-26
R17 | M1: Destination + Reviews | Task | Functional QA | Execute account, review, moderation and rating tests | Md. Irfan Iqbal | All | 6 | 2026-10-20 | 2026-10-31 | R04,R07,R11 | Not started | Pass/fail evidence and defect records complete | Retest critical fixes | bar: 2026-10-19 to 2026-10-26
R18 | M1: Destination + Reviews | Task | Offline QA | Test airplane mode, weak network, Bangla and storage failure | Md. Irfan Iqbal | Abdullah | 6 | 2026-10-23 | 2026-11-01 | R12,R13,R15 | Not started | Real-device evidence for download/open/reconnect | Include denied persistence and stale pack | bar: 2026-10-19 to 2026-10-26
R19 | M1: Destination + Reviews | Task | Release coordination | Run integration, defect triage and scope control | Shahriar Islam | All | 5 | 2026-10-25 | 2026-11-01 | R03,R11,R13 | Not started | No blocker in destination-review-offline flow | Cut quantity before lifecycle | bar: 2026-10-19 to 2026-10-26
R20 | M1: Destination + Reviews | Task | Acceptance QA | Run M1 acceptance regression and prepare test summary | Md. Irfan Iqbal | All | 4 | 2026-10-30 | 2026-11-02 | R17,R18,R19 | Not started | Signed acceptance checklist and known limitations | Evidence linked by test ID | bar: 2026-10-26 to 2026-11-02
M1 | M1: Destination + Reviews | Milestone | Gate | Major feature accepted: destination + reviews + bilingual offline support | Shahriar Islam | All | 1 | 2026-11-02 | 2026-11-02 | R20 | Not started | End-to-end demonstration succeeds | Fixed milestone | bar: 2026-11-02
E01 | M2: Estimator + 55% | Task | Estimator design | Freeze rule engine, pricing units, confidence and scope | Shahriar Islam | Muhtasim, Irfan | 5 | 2026-11-03 | 2026-11-08 | M1 | Not started | Rule specification and worked examples approved | No ML | bar: 2026-11-02
E02 | M2: Estimator + 55% | Task | Seed research | Research destination A prices and advisories | Shahriar Islam | Irfan | 4 | 2026-11-03 | 2026-11-14 | E01 | Not started | Source/date/unit/tier/season recorded | Validation trips excluded | bar: 2026-11-02 to 2026-11-09
E03 | M2: Estimator + 55% | Task | Seed research | Research destination B prices and advisories | Abdullah Bin Sorwar Choudhury | Shahriar | 4 | 2026-11-03 | 2026-11-14 | E01 | Not started | Source/date/unit/tier/season recorded | Validation trips excluded | bar: 2026-11-02 to 2026-11-09
E04 | M2: Estimator + 55% | Task | Seed research | Research destination C prices and advisories | Syed Muhtasim Alam | Shahriar | 4 | 2026-11-03 | 2026-11-14 | E01 | Not started | Source/date/unit/tier/season recorded | Validation trips excluded | bar: 2026-11-02 to 2026-11-09
E05 | M2: Estimator + 55% | Task | Seed research | Research destination D prices and advisories | Md. Irfan Iqbal | Shahriar | 4 | 2026-11-03 | 2026-11-14 | E01 | Not started | Independent source/date/unit/tier/season review | Validation trips remain sealed | bar: 2026-11-02 to 2026-11-09
E06 | M2: Estimator + 55% | Task | Pricing catalogue | Implement pricing catalogue, units, season and freshness model | Syed Muhtasim Alam | Shahriar | 6 | 2026-11-09 | 2026-11-22 | E01,E02,E03,E04,E05 | Not started | Per-person/room/vehicle/group/day rules tested | Official fixed prices take priority | bar: 2026-11-09 to 2026-11-16
E07 | M2: Estimator + 55% | Task | Estimator API | Implement itemized rule engine and confidence calculation | Syed Muhtasim Alam | Irfan | 7 | 2026-11-16 | 2026-11-29 | E06 | Not started | Representative hand calculations match API | Stale flagged; expired excluded | bar: 2026-11-16 to 2026-11-23
E08 | M2: Estimator + 55% | Task | Estimator UI | Build traveller-context input and itemized result screens | Abdullah Bin Sorwar Choudhury | Muhtasim | 7 | 2026-11-16 | 2026-11-30 | E01,E07 | Not started | Shows assumptions, sources, dates and confidence | Works in Bangla and English | bar: 2026-11-16 to 2026-11-30
E09 | M2: Estimator + 55% | Task | Saved trip brief | Save estimate, notes and optional contacts; include in offline pack | Abdullah Bin Sorwar Choudhury | Muhtasim, Irfan | 5 | 2026-11-23 | 2026-12-03 | E08,R13 | Not started | Reopen/copy/delete works online and offline | Not a day-by-day itinerary | bar: 2026-11-23 to 2026-11-30
E10 | M2: Estimator + 55% | Task | Admin data | Build minimal price/advisory maintenance interface | Shahriar Islam | Muhtasim | 6 | 2026-11-16 | 2026-11-30 | E06 | Not started | Admin can update source, date and expiry | Audit actor and timestamp retained | bar: 2026-11-16 to 2026-11-30
E11 | M2: Estimator + 55% | Task | Estimator QA | Create hand-calculated scenarios, baseline and held-out protocol | Md. Irfan Iqbal | Shahriar | 6 | 2026-11-09 | 2026-11-24 | E01 | Not started | Test dataset separated from seed data | Baseline does not use held-out trips | bar: 2026-11-09 to 2026-11-23
E12 | M2: Estimator + 55% | Task | Estimator QA | Execute calculation, stale-data and confidence tests | Md. Irfan Iqbal | Muhtasim | 6 | 2026-11-23 | 2026-12-04 | E07,E11 | Not started | All pricing units and edge cases recorded | Compare representative output to baseline | bar: 2026-11-23 to 2026-11-30
E13 | M2: Estimator + 55% | Task | Integration | Integrate estimator, saved brief, review and offline flows | Abdullah Bin Sorwar Choudhury | Muhtasim, Shahriar | 5 | 2026-11-28 | 2026-12-05 | E08,E09,E10 | Not started | One continuous user journey passes | No regression in M1 | bar: 2026-11-23 to 2026-11-30
E14 | M2: Estimator + 55% | Task | Release coordination | Run progress audit, defect triage and evidence pack | Shahriar Islam | All | 5 | 2026-11-30 | 2026-12-06 | E10,E12,E13 | Not started | Acceptance checklist demonstrates 50-60% scope | Deferred items documented | bar: 2026-11-30
M2 | M2: Estimator + 55% | Milestone | Gate | Significant progress checkpoint: 50-60% complete | Shahriar Islam | All | 1 | 2026-12-07 | 2026-12-07 | E14 | Not started | Instructor-ready integrated demonstration | Fixed milestone | bar: 2026-12-07
H01 | Hardening | Task | Content | Add and quality-check remaining MVP destinations | Shahriar Islam | All | 6 | 2026-12-08 | 2026-12-20 | M2 | Not started | Each destination meets source/date/licence rules | Quantity may be cut before quality | bar: 2026-12-07 to 2026-12-14
H02 | Hardening | Task | Review UX | Improve review transparency, filtering and rating explanation | Abdullah Bin Sorwar Choudhury | Shahriar | 5 | 2026-12-08 | 2026-12-18 | M2 | Not started | Counts, context and moderation state are clear | No sponsorship effect on rating | bar: 2026-12-07 to 2026-12-14
H03 | Hardening | Task | Offline reliability | Harden cache versioning, invalidation and storage recovery | Abdullah Bin Sorwar Choudhury | Muhtasim, Irfan | 6 | 2026-12-08 | 2026-12-24 | M2 | Not started | Old packs refresh safely; refusal/eviction handled | Test on real Android | bar: 2026-12-07 to 2026-12-21
H04 | Hardening | Task | Backend reliability | Add pagination, structured errors, logging and retry safety | Syed Muhtasim Alam | Irfan | 6 | 2026-12-08 | 2026-12-22 | M2 | Not started | Load/error/idempotency tests pass | No sensitive data in logs | bar: 2026-12-07 to 2026-12-21
H05 | Hardening | Task | Security | Harden sessions, CSRF/origin policy and role permissions | Syed Muhtasim Alam | Irfan | 6 | 2026-12-15 | 2026-12-27 | F07,H04 | Not started | Security checklist and negative tests pass | Document dev/prod differences | bar: 2026-12-14 to 2026-12-21
H06 | Hardening | Task | Administration | Polish moderation and source-maintenance workflow | Shahriar Islam | Abdullah | 5 | 2026-12-15 | 2026-12-27 | E10,H02 | Not started | Admin tasks are usable and auditable | Manual verification stated | bar: 2026-12-14 to 2026-12-21
H07 | Hardening | Task | Automation QA | Expand automated regression and smoke-test suite | Md. Irfan Iqbal | Abdullah, Muhtasim | 5 | 2026-12-08 | 2026-12-27 | M2 | Not started | Core API/UI checks run repeatably | Track flaky tests | bar: 2026-12-07 to 2026-12-21
H08 | Hardening | Task | Usability QA | Run pilot with at least eight consenting participants | Md. Irfan Iqbal | Shahriar | 5 | 2026-12-15 | 2026-12-29 | H01,H02 | Not started | Includes Bangla-preferring and less technical users | Retain only necessary study data | bar: 2026-12-14 to 2026-12-28
H09 | Hardening | Task | Accessibility | Fix keyboard, readability, responsive and Bangla-rendering issues | Abdullah Bin Sorwar Choudhury | Irfan | 5 | 2026-12-21 | 2027-01-02 | H02,H08 | Not started | Target flows usable on low-end Android | Record remaining limitations | bar: 2026-12-21 to 2026-12-28
H10 | Hardening | Task | Test readiness | Prepare frozen test build, data, environment and procedures | Md. Irfan Iqbal | All | 5 | 2026-12-28 | 2027-01-03 | H03,H04,H05,H07 | Not started | Versioned build and test briefing ready | No untriaged blocker | bar: 2026-12-28
H11 | Hardening | Task | Release readiness | Prepare deployment, recovery, setup and operator documentation | Shahriar Islam | Muhtasim | 5 | 2026-12-21 | 2027-01-03 | H04,H06 | Not started | Fresh setup and recovery rehearsal succeed | Name post-semester data owner | bar: 2026-12-21 to 2026-12-28
G1 | Hardening | Gate | Gate | Testing-entry readiness review | Shahriar Islam | All | 1 | 2027-01-03 | 2027-01-03 | H10,H11 | Not started | Build, data, RTM and environment approved | No scope additions after gate | bar: 2026-12-28
T01 | Formal Testing | Task | Test control | Freeze build and brief testers on data, environment and defects | Shahriar Islam | Irfan | 3 | 2027-01-04 | 2027-01-04 | G1 | Not started | Build ID and briefing record published | Changes require defect reference | bar: 2027-01-04
T02 | Formal Testing | Task | Test management | Finalize RTM, master register and execution records | Md. Irfan Iqbal | All | 5 | 2027-01-04 | 2027-01-05 | H10 | Not started | Every in-scope requirement has test IDs | Templates include evidence/retest fields | bar: 2027-01-04
T03 | Formal Testing | Task | Functional QA | Execute destination-estimate-offline-review full flow | Md. Irfan Iqbal | All | 6 | 2027-01-05 | 2027-01-08 | T02 | Not started | Actual results and evidence recorded per case | Cover reconnect and moderation | bar: 2027-01-04
T04 | Formal Testing | Task | Non-functional QA | Execute 2G/3G, airplane, device, accessibility and privacy tests | Md. Irfan Iqbal | Abdullah, Muhtasim | 6 | 2027-01-05 | 2027-01-09 | T02 | Not started | Environment and metrics recorded | Private API data not publicly cached | bar: 2027-01-04
T05 | Formal Testing | Task | Frontend fixes | Resolve assigned UI, bilingual and offline defects | Abdullah Bin Sorwar Choudhury | Irfan | 6 | 2027-01-06 | 2027-01-10 | T03,T04 | Not started | Critical/high frontend defects retested | No unrelated feature work | bar: 2027-01-04
T06 | Formal Testing | Task | Backend fixes | Resolve assigned API, security and data defects | Syed Muhtasim Alam | Irfan | 6 | 2027-01-06 | 2027-01-10 | T03,T04 | Not started | Critical/high backend defects retested | Migration remains reproducible | bar: 2027-01-04
T07 | Formal Testing | Task | Content/admin fixes | Resolve data, advisory and moderation defects | Shahriar Islam | Irfan | 5 | 2027-01-06 | 2027-01-10 | T03,T04 | Not started | Source/freshness/admin defects retested | All changes documented | bar: 2027-01-04
T08 | Formal Testing | Task | Regression QA | Retest fixes and run affected-flow regression | Md. Irfan Iqbal | All | 6 | 2027-01-08 | 2027-01-11 | T05,T06,T07 | Not started | No blocker/critical defect in core flow | Lower severity documented | bar: 2027-01-04 to 2027-01-11
T09 | Formal Testing | Task | Exit QA | Complete SQA summary and exit recommendation | Md. Irfan Iqbal | Shahriar | 4 | 2027-01-11 | 2027-01-11 | T08 | Not started | Coverage, defects and residual risks reported | Formal testing ends 11 Jan | bar: 2027-01-11
M3 | Formal Testing | Milestone | Gate | Formal testing completed | Md. Irfan Iqbal | All | 1 | 2027-01-11 | 2027-01-11 | T09 | Not started | Exit criteria approved | Fixed milestone | bar: 2027-01-11
C01 | Completion | Task | Frontend release | Close remaining approved UI defects and freeze client | Abdullah Bin Sorwar Choudhury | Irfan | 5 | 2027-01-12 | 2027-01-15 | M3 | Not started | Release candidate has no open blocker | Only approved fixes | bar: 2027-01-11
C02 | Completion | Task | Backend release | Close remaining approved backend defects and freeze services | Syed Muhtasim Alam | Irfan | 5 | 2027-01-12 | 2027-01-15 | M3 | Not started | Migration/deployment/recovery verified | Only approved fixes | bar: 2027-01-11
C03 | Completion | Task | Content release | Freeze destination, price and advisory content | Shahriar Islam | Irfan | 4 | 2027-01-12 | 2027-01-15 | M3 | Not started | Sources and last-updated dates complete | Expired items excluded | bar: 2027-01-11
C04 | Completion | Task | Final QA | Run release-candidate smoke test and verify evidence archive | Md. Irfan Iqbal | All | 5 | 2027-01-15 | 2027-01-16 | C01,C02,C03 | Not started | Release candidate and evidence signed off | Record residual risks | bar: 2027-01-11
C05 | Completion | Task | Documentation | Finalize report, setup guide, limitations and maintenance plan | Shahriar Islam | All | 5 | 2027-01-12 | 2027-01-16 | M3 | Not started | Submission package is internally consistent | Post-semester ownership named | bar: 2027-01-11
C06 | Completion | Task | Demonstration | Prepare and rehearse timed final demonstration | Shahriar Islam | All | 4 | 2027-01-15 | 2027-01-17 | C04,C05 | Not started | Backup demo and recovery path tested | Each member owns a segment | bar: 2027-01-11
C07 | Completion | Task | Delivery support | Prepare stable demo build and backup deployment | Syed Muhtasim Alam | Abdullah | 4 | 2027-01-15 | 2027-01-17 | C02,C04 | Not started | Primary and backup environments verified | No live payment dependency | bar: 2027-01-11
C08 | Completion | Task | Presentation UI | Prepare final screenshots and bilingual demo data | Abdullah Bin Sorwar Choudhury | Shahriar | 4 | 2027-01-15 | 2027-01-17 | C01,C03 | Not started | Screens and data match release candidate | No fake live claims | bar: 2027-01-11
M4 | Completion | Milestone | Gate | Final project completion | Shahriar Islam | All | 1 | 2027-01-17 | 2027-01-18 | C04,C06,C07,C08 | Not started | Project completed by 17/18 Jan 2027 | Fixed milestone | bar: 2027-01-11 to 2027-01-18
Workload balance — primary-owner effort points
Owner | Role | Primary tasks | Effort points | Share |  | Balance check | Target
Shahriar Islam | Project leader / content / moderation | 22 | 87 | 25% |  | 0 | 0 points
Abdullah Bin Sorwar Choudhury | Frontend / bilingual / offline | 17 | 87 | 25%
Syed Muhtasim Alam | Backend / data / security | 17 | 87 | 25%
Md. Irfan Iqbal | SQA / test management | 18 | 87 | 25%
Workload note | Primary effort is 87 points per member; each member holds 25.0%. Support work is collaborative and is not double-counted.